## Tabelle1
Use Case | Time Spent | Story Points
Login | 9.5 | 13
Register | 9.57 | 13
Leader Board | 2.52 | 8
Play Solo | 29.67 | 21
Edit User | 0 | 3
Delete User | 0 | 3
Use Case (upcoming) | Estimated Time
Create Lobby | 24.32 | 21
Player vs. Lobby | 24.32 | 21
Edit Profile | 15.06 | 13
View Profile | 5.79 | 5
Delete Account | 3.48 | 3